## Slide 1
Step-wise: An overview of project planning

## Slide 2
Project Planning
Step-0: Select Project

## Slide 3
Project Planning
Step-1: Identify Project Scope and Objectives
1.1 Identify objectives and measures of effectiveness
Objective: Automate attendance tracking.
Measure: Reduce manual errors by 90% within 3 months.
1.2 Establish a project authority
Example: The Head of the CSE Department is appointed as the project authority.
1.3 Identify stakeholders and their interests
Faculty: Quick and easy attendance marking.
Students: View attendance history.
Admin: Generate monthly reports.

## Slide 4
Project Planning
1.4 Modify objectives in light of stakeholder analysis
Example: Add feature to send SMS/email alerts for low attendance.
1.5 Establish communication methods with all parties
Example: Weekly Zoom reviews, Google Drive for documents, WhatsApp group for urgent queries.
2

## Slide 5
Project Planning
Step-2: Identify Project Infrastructure
Focuses on setting up the environment in which the project will be developed.
Deals with aligning the project with organizational goals, setting technical standards, and organizing the project team.
2.1 Establish Relationship Between Project and Strategic Planning
Understand how the project fits into the organization’s long-term goals or strategic vision.
Example: If the college has a digital transformation strategy, the Attendance Management System should align with it (e.g., integrate with student portals).

## Slide 6
Project Planning
2.2 Identify Installation Standards and Procedures
Determine which technologies, platforms, coding standards, and installation protocols should be followed.
Example: Use institution-approved technologies like Python, MySQL for database, and follow ISO software testing standards.
2.3 Identify Project Team Organization
Define the project team structure—roles, reporting relationships, and communication paths.
Example:
  Project Manager: Oversees the timeline and coordination.
  Developers: Handle design and coding.
  Testers: Perform validation and verification.
  Faculty Advisor: Reviews and approves major decisions.

## Slide 7
Project Planning
Step-3: Analyze project characteristics
3.1 Distinguish the project as either objective-driven or product-driven
Objective-driven: Focus is on achieving a goal (e.g., improve customer service).
Product-driven: Focus is on delivering a specific product (e.g., develop a payroll system).
3.2 Analyse other project characteristics
Consider:
  Is it an information system (for managing data)?
  A process control system (e.g., controlling equipment)?
  A safety-critical system (where failure could harm people)?

## Slide 8
Project Planning
3.3 Identify high-level project risks
Think about what might go wrong and impact success.
Risks may arise from:
  Development environment (e.g., unfamiliar tech)
  Product nature (e.g., complex payroll system)
  People issues (e.g., user resistance to change)
3.4 Take user requirements into account
Users may have specific implementation expectations.
Government departments might demand formal procedures

## Slide 9
Project Planning
3.5 Select general lifecycle approach
Choose a lifecycle model that best fits the above characteristics and risks:
  e.g., Waterfall, Incremental, Spiral, Agile, etc.
3.6 Review overall resource estimates

## Slide 10
Project Planning
Step-4: Identify project products and activities
4.1 Identify and describe the project products (or deliverables)
Every project must produce deliverables
This step is about listing and describing all those deliverables the project is expected to create.
It ensures that every activity in the project leads to a clear product, and no activity is done without purpose.
Technical Products
  Examples: Code, system components, training material, operation manuals.
Management Products
  Examples: Progress reports, work breakdown structure (WBS)
Quality Products
  Examples: Test plans, quality assurance checklists, standards compliance documents.

## Slide 11
Project Planning
4.2 Document generic product flows
  A Product Flow Diagram (PFD) visually shows the logical sequence in which project deliverables (products) must be created.

## Slide 12
Project Planning
4.2 Document generic product flows

## Slide 13
Project Planning
4.3 Recognize Product Instances
  Sometimes, a general idea or module (called a “generic product”) can have multiple versions or pieces (called “instances”).
4.4 Produce Ideal Activity Network
What it means: To go from one product (or step) to another, we need a set of activities. This step is about:
Listing what tasks need to be done
Putting them in correct order
Creating an activity network (like a flowchart)

## Slide 14
Project Planning
4.5 Modify the Ideal to Take into Account Need for Stages and Checkpoints
5: Estimate Effort for Each Activity
5.1: Carry Out Bottom-Up Estimates
What it means: Estimate the effort (like staff time, resources) needed for each individual task/activity in the project.
Bottom-up estimation involves:
  Starting from the lowest level (individual tasks).
  Adding up the effort to get the total estimate for the project.
These estimates will:
  Be based on the type of task (e.g., coding, testing).
  Help calculate the total elapsed time for the project.

## Slide 15
Project Planning
5.2 : Revise Plan to Create Controllable Activities
Why revise? Some tasks might be too long or too vague, making it hard to track progress.
Example: Suppose a task like “System Testing” is estimated to take 12 weeks. After 6 weeks, it's hard to tell if 50% of testing is actually done.
Solution: Break long activities into smaller, manageable sub-tasks (e.g., “Login module testing,” “Payment module testing”).
Benefits:
Makes tracking progress easier.
Helps in early detection of delays.

## Slide 16
Project Planning
6 Identify activity risks
6.1: Identify and Quantify Activity-Based Risks
This step involves identifying specific risks for each activity in the project. For every task or activity, we analyze:
What could go wrong?
How likely is it to happen? (Likelihood)
How bad would it be if it happened? (Impact)

## Slide 17
Project Planning
6.2: Plan Risk Reduction and Contingency Measures
how to reduce the chance of the risk happening (risk reduction), and what to do if it does happen (contingency plan).
Example
Continuing the login module risk from Step 6.1:
Risk Reduction: Assign a second developer to learn the login module code (backup).
Contingency Plan: If the main developer is unavailable, the backup will take over, or a freelancer will be hired.

## Slide 18
Project Planning
6.3: Adjust Overall Plans and Estimates to Take Account of Risks
After identifying risks and planning responses, adjust your project schedule, budget, or resources to reflect these risks.
Makes plan more realistic and less likely to fail.
Example:
Because the login module is risky:
Add 2 extra buffer days to the schedule.
Allocate training time for the backup developer.

## Slide 19
Project Planning
7 Allocate Resources
7.1: Identify and Allocate Resources
This step involves identifying what resources (mainly staff or team members) are needed to complete each activity. It ensures the right people are assigned to the right tasks.
Example:
For a student attendance tracking system, you might assign:
  Developer A for frontend UI
  Developer B for backend logic
  Tester C for module testing
Each team member is provisionally assigned based on their skills and availability.

## Slide 20
Project Planning
7.2: Revise Plans and Estimates to Take Resource Constraints into Account
Sometimes, the same person may be needed for multiple tasks at the same time. Since a person can’t work on two things simultaneously, you need to set priorities and adjust the timeline.
Example:
Developer A is assigned to both:
  Design UI for login module
  Build dashboard module
If both tasks are scheduled to happen at the same time, one must be delayed or given to someone else. This will affect the overall project duration.

## Slide 21
Project Planning
8 Review Plan
8.1 Review Quality Aspects of the Project Plan
During project execution, it’s possible to discover that earlier tasks were not properly completed. If such issues are not caught early, they may cause major delays or failures later. Therefore, each task must be checked for quality before marking it as done.
These checks are called “exit requirements” – standards or conditions that a task must meet before it can be signed off.

## Slide 22
Project Planning
8.1 Review Quality Aspects of the Project Plan
Example:
Suppose a task is to create a login page for an application.
The exit requirements might include:
  Page loads in less than 2 seconds
  Validation for username and password works
  Errors are displayed properly for invalid input
  Code is peer-reviewed and approved
If any of these checks fail, the task should not be considered complete, even if the coding is done.

## Slide 23
Project Planning
8.2: Document Plans and Obtain Agreement
All the plans prepared for the project must be clearly documented and shared with all stakeholders (e.g., team members, clients, management).
Everyone involved must:
Understand what the project requires
Agree to their responsibilities
This helps avoid confusion later.
Example:
You plan to launch a new student attendance system. Before starting:
You write down the plan for design, development, and testing
You send the plan to the client and your team
They review and agree to the timeline and their roles

## Slide 24
Project Planning
9 Execute Plan
The tasks described in the plan are carried out. The project manager:
Monitors progress
Ensures tasks are done on time
Handles any issues that arise
Example:
The development team begins coding the login module. The manager checks:
Is it being done according to plan?
Are there any delays?

## Slide 25
Project Planning
10 Lower Levels of Planning
As the project progresses, detailed planning is needed for upcoming tasks. Early-stage tasks can be fully planned in advance, but later-stage tasks might be planned in more detail as the project moves forward, since more information will be available by then.
This is called progressive elaboration.
Example:
You don’t need to plan the entire reporting module in detail at the start. Once the database and user modules are complete, you’ll have a better idea of how the reporting module should work and can plan it then.